## Autumn Overview
LAUNCH PATHWAY — AUTUMN 1 YEAR PLAN (ASDAN) · 2026/27
Progress Schools Tees Valley · LAUNCH pathway · Teacher: M Roper · linked to LAUNCH KS4 - 2026-27. No pupil names in this workbook — for the class roster see the weekly planner (Students sheet).
⚠ Built from the deployed 2026-27 LAUNCH lessons at commit f8c4bd6. PEQ unit codes, criterion structure and credit values are provisional - not yet verified against the official ASDAN specification, and cohort registration is not confirmed. Do not promise pupils accreditation on the basis of this plan. Reconcile at the spec check before assessment begins.
Wk | w/c | Science (Teesside · GCSE Biology) | ASDAN PEQ — ComSk1 | Humanities (LAUNCH) | Arts (Trinity Silver)
1 | 1 Sep | Baseline — no ASDAN assessment (cohort not yet registered); science baseline assessments | Intro & choosing my level — baseline self-assessment (ComSk1 begins; no assessment until registered) | Source Investigation | Frame the Local Challenge (Unit 1)
2 | 7 Sep | Baseline | What makes communication effective (audience & purpose; formal / informal) | Cause & Consequence Courtroom | Practice, Careers & Pathways (Unit 1)
3 | 14 Sep | Cells under the microscope — magnification and why resolution matters | Active listening & giving feedback | Archive: nature, origin & purpose | Implement & Critically Develop (Unit 1)
4 | 21 Sep | Diffusion — and the factors that affect its rate | Plan a communication activity (SMART) — PLAN CREATED | Century of Change | Arts Experience: Attend, Analyse & Share (Unit 1)
5 | 28 Sep | Osmosis — and how it differs from diffusion | Deliver the activity & gather evidence — PLAN LIVE, 10-hr clock; min 3-min talk OR 250-word text | People & Modern Britain (migration) | Design the Leadership Project (Unit 2)
6 | 5 Oct | Active transport — and how it differs from diffusion and osmosis | Review progress & sign off the unit | Structured Account | Pilot, Lead & Adapt (Unit 2)
7 | 12 Oct | Topic 1 knowledge round-up (microscopy · diffusion · osmosis · active transport) + exam skills | Consolidation & gap-fill — 10-hr tally continues [pattern from BUILD; not in the LAUNCH SoW] | Source Assessment ★ ASSESSED | Deliver & Curate the Arts Project (Unit 2)
8 | 19 Oct | AUT 1 consolidation / assessment [no separate built science lesson — term-shape week] | AUDIT — ComSk1 evidence complete & signed before half term [pattern from BUILD; not in the LAUNCH SoW] | OS Map Skills: unfamiliar problem | Review, Influence & Portfolio Audit (Unit 2)
— | 26–30 Oct | HALF TERM (26–30 Oct, Redcar & Cleveland draft calendar)
LAUNCH content in this plan is Autumn 1 only. Autumn 2 (from w/c 2 Nov) and Spring/Summer are a separate future build (same generator) — this overview does not fabricate weeks that are not yet authored.
Legend: ★ = assessed in exam-style conditions. Shaded W1–W2 = baseline (no ASDAN assessment — cohort must be registered first). PEQ W7–W8 mirror BUILD's consolidation/audit pattern (not separately in the LAUNCH SoW). Arts follows the deployed LAUNCH Art SoW: Unit 1 W1–4, Unit 2 W5–8, all Autumn 1.

## PEQ Evidence Map
ComSk1 — COMMUNICATION SKILLS · Level 1 · 3 credits / 27 GLH
⚠ Built from the deployed 2026-27 LAUNCH lessons at commit f8c4bd6. PEQ unit codes, criterion structure and credit values are provisional - not yet verified against the official ASDAN specification, and cohort registration is not confirmed. Do not promise pupils accreditation on the basis of this plan. Reconcile at the spec check before assessment begins. The deployed lessons carry only the unit code ComSk1 (no sub-criterion codes); the spine below is derived from the lesson sequence. L1 command verbs: Outline / Describe / Give examples.
ComSk1 spine (step) | What it covers | Week(s) | w/c | Minimum evidence
Baseline / choose level | Name the six PEQ skills; self-assess honestly; choose my level | W1 | 1 Sep | Self-assessment + chosen level, photographed into portfolio (no assessment until registered)
Know — effective communication | What makes communication effective; audience & purpose; formal / informal | W2 | 7 Sep | Examples of formal and informal communication (Outline / Describe / Give examples)
Know — active listening & feedback | Active listening; giving clear, kind feedback; checking understanding | W3 | 14 Sep | Feedback given with examples; scribed note of how understanding was checked
Plan (SMART) | Write a SMART plan for a communication activity | W4 | 21 Sep | SMART plan naming audience, purpose and success; outline of the evidence to collect. PLAN CREATED
Plan live — deliver & use | Deliver the activity to my audience; gather evidence; plan used across the weeks | W5 | 28 Sep | Delivery meeting the ComSk1 minimum — a talk of ≥3 minutes OR a written text of ≥250 words; dated & witnessed. PLAN LIVE — 10-hr clock starts (fixed)
Use over ≥10 hours | Plan used over a minimum of 10 hours | W5–W7 | 28 Sep–12 Oct | 10-hour tally logged ACROSS THE WHOLE TIMETABLE by every adult — not the ASDAN slot alone
Review & sign off | Review my own success; what went well and one area to develop | W6 → W8 | 5 Oct / 19 Oct | Review completed and signed by assessor AND learner before half term; portfolio → Evidence Binder
THE 10-HOUR RULE IS THE DESIGN CONSTRAINT
ComSk1 requires the plan to be USED over a minimum of 10 hours. Those hours accrue across the WHOLE timetable, not the ASDAN slot alone. The plan goes live on a fixed week (w/c 28 Sep) so 10 hours can accrue before the signed review, which completes before the final Aut 1 teaching week (w/c 19 Oct). Brief every adult on the tally before the plan goes live. Note: the deployed lessons state the 3-min / 250-word minimum; a minimum team size is not specified in the built lessons — confirm at the spec check.
PATHWAY TO THE AWARD
The full-year LAUNCH SoW homes all six Level 1 units, so the ceiling is a PEQ Level 1 Certificate. This workbook covers AUTUMN ONLY and banks ComSk1 (3 credits). Do not present the Certificate as achieved by this term's work. E3–L1 only in 2026/27; the Stretch tier is written to an L2 evidence standard (stretch language only — no L2 registration is claimed).

## Key Dates & Compliance
KEY DATES & COMPLIANCE · LAUNCH · Autumn 2026
TERM SHAPE (Redcar & Cleveland 2026–27 DRAFT calendar — reconfirm when final)
Term | 1 Sep – 18 Dec 2026. FIFTEEN weeks: Aut 1 = 8 weeks, Aut 2 = 7 weeks. LAUNCH content in this plan is Autumn 1.
W1–W2 | Baseline — w/c 1 & 7 Sep. Boxall / GL / BKSB and subject baselines. NO ASDAN assessment.
W3 | ComSk1 teaching underway — w/c 14 Sep.
W5 | w/c 28 Sep — PLAN LIVE. 10-hour clock starts. This date is fixed.
W7 | w/c 12 Oct — consolidation & gap-fill (pattern from BUILD; not separately in the LAUNCH SoW).
W8 | w/c 19 Oct — LAST WEEK OF AUT 1. Audit: ComSk1 evidence complete & signed.
Half term | 26–30 Oct.
QUALIFICATION PATHWAY (per the LAUNCH SoW)
Science | GCSE Biology (Pearson 1BI0, Foundation) or Combined Science (Pearson 1SC0, Foundation); the IGCSE suite as an optional stretch for eligible students.
English | AQA English Language 8700; optional AQA English Literature 8702 and AQA Entry Level Certificate 8145.
Arts | Trinity Arts Award Silver (Unit 1 + Unit 2).
ASDAN PEQ | Personal Effectiveness — Entry 3 to Level 1 only in 2026/27 (ComSk1 this term). Other strands bank ASDAN short courses + AQA Unit Award Scheme.
⚠ ADMIN — DO THESE
September | REGISTER THE COHORT WITH ASDAN before any assessment takes place. No evidence counts until registration is complete. (Cheryl's decision — still open.)
Jan/Feb 2027 | BOOK FIRST-YEAR EQA SAMPLING. Required in year one even with no completers.
Before w/c 28 Sep | Brief every adult on the 10-hour tally before the plan goes live.
Every review | Assessment records signed by BOTH assessor AND learner.
If outstanding | Book the Trinity Arts Award adviser training (Discover & Explore / Silver).
Class roster, access and individual-needs notes are NOT in this distributed file — they live in the weekly planner's Students sheet.

## Slot Plan Aut1
LAUNCH five-strand provision — Aut 1 (2026-27)
'I can…' outcomes taken verbatim from each built LAUNCH lesson at commit f8c4bd6. Strands run W1–W6 in the LAUNCH SoW; W7–W8 mirror BUILD's consolidation + audit pattern and are NOT separately specified in the LAUNCH Aut 1 SoW. No pupil names — roster lives in the weekly planner.
Wk | w/c | PEQ | Careers | Independent Living | Vocational | Community & Enterprise
1 | 1 Sep | I can name the six PEQ skills | I can name my skills, interests and strengths | I can describe a daily self-care routine | I can name common vocational skills | I can spot a real need in my community
2 | 7 Sep | I can outline what makes communication effective | I can name several job sectors | I can spot common home hazards | I can name key workplace safety rules | I can turn a need into a project aim
3 | 14 Sep | I can outline what active listening looks like | I can say what labour-market information is | I can sort and wash laundry safely | I can follow a set of instructions in order | I can take a clear role in the project team
4 | 21 Sep | I can write a SMART plan for a communication activity | I can prepare questions for an employer | I can plan a cleaning routine for a room | I can take a clear role in a team task | I can name a partner who could help
5 | 28 Sep | I can deliver my communication activity to my audience | I can match my profile to a real opportunity | I can name key personal documents | I can name tools for a vocational task | I can carry out my role in delivery
6 | 5 Oct | I can review my own success in communicating | I can set a SMART careers target | I can plan a balanced meal using the Eatwell guide | I can complete a vocational task from start to finish | I can create a clear message about our project
7 | 12 Oct | Consolidation & gap-fill — complete and file W1–W6 evidence* | Consolidation & gap-fill — complete and file W1–W6 evidence* | Consolidation & gap-fill — complete and file W1–W6 evidence* | Consolidation & gap-fill — complete and file W1–W6 evidence* | Consolidation & gap-fill — complete and file W1–W6 evidence*
8 | 19 Oct | Audit before half term — evidence complete & signed* | Audit before half term — evidence complete & signed* | Audit before half term — evidence complete & signed* | Audit before half term — evidence complete & signed* | Audit before half term — evidence complete & signed*
* W7–W8 apply BUILD's structural consolidation/audit pattern; they are not separately specified in the LAUNCH Aut 1 SoW (which defines W1–W6). Confirm the exact W7–W8 activities with Matt.